## Sheet1
Risk Register for Expense Tracker
05/28/2020
Project Name: Expense Tracker
ID No. | Rank | Risk | Description | Category | Root Cause | Triggers | Potential Responses | Risk Owner | Impact | Status
111 | 1 | Cash Flow | There should be high amount of Firm as we are a Money management. So without firm, it would be a highest risk. | Financial Risk | Deficeit in Money | Salary Increments | Risk Acceptance | Finance Expert | High | Anticipated
112 | 2 | Resources and Team | If there are no resources like employees there will be loss to company. | People Risk | Lack of resources with proper skill set | Dissatisfaction of Employees | Risk Mitigation | Project Manager | Medium | Anticipated
113 | 3 | Scope | When there is no scope to predict the quality, budget and resources, then there can be a huge risk | Structure/Process risk | Wrong estimation | Client Dissatisfaction | Risk avoidance | Project Manager | High | Avoided
114 | 4 | Stakeholders | If stakeholders has negative attitude towards a project or no cooperation between them, then it is a road block to the project. | Process Risk | Lack of cooperation between stakeholders | Meeting Reviews | Risk avoidance | Program Manager/ Programmer | Medium | Mitigated
115 | 5 | Existence of similar software in the market | When there is a similar Money Management firm, due to this there can be a competition and can reduce the popularity of the company. | Market Risk | Availability of similar products in the market | Application | Risk Acceptance | Manager/ Programmer | Medium | Anticipated
116 | 6 | Recession in market | Fluctuating market demands that cause shares to increase and decrease without any specific pattern. | Market Risk | Recession | Lacking of proactiveness on analying market | Risk Acceptance | Finance Expert | Medium | Anticipated
117 | 7 | Natural Disasters | Climatic conditions are out of our hands, so we need to take specific measures or mitigation plans to avoid them. | Financial Risk | Being not ready to face the risk | No before proper preparations | Risk Acceptance | All | High | Anticipated
118 | 8 | Late completion of testing | Risk chances are high. Guarantee legitimate observing set up and utilized adequately. | Process Risk | Time constraints would not be same | Lacking of time in schedules | Risk Acceptance | Project Manager | High | Mitigated
119 | 9 | Defective Server | Risk chances are high. Have reinforcement servers in position, assess a warm site business recuperation plan. | Process Risk | Main server crash would cause business losses | No proper backups | Risk Acceptance | Project Manager | High | Anticipated
120 | 10 | Executive Support | Risk chances are more. Weak executive support is the biggest risk. There ought to be explicit duties for the project from the top level administration. | Structure/Process risk | Commitment from executives | Dissatisfaction of executives | Risk Avoidance | Project Manager | High | Avoided